Business Analysis – Agile & Scrum Activity

1. Business Situation

The company in this scenario is called FreshMart, a local grocery chain with 10 stores. Over the past year, the business has been losing money. Customers are complaining, sales are going down, and the management does not know exactly what is going wrong.

Here are some of the problems the company is facing:

- Sales have dropped by 20% compared to last year.

- Customers are leaving bad reviews online about long waiting times at checkout.

- A lot of food items are expiring before they get sold, which is causing waste and losses.

- Staff turnover is high — many employees keep quitting after a short time.

- The website is slow and customers find it hard to place online orders.

2. Descriptive Statistics

Below is a simple summary of FreshMart's numbers over the past three months to show how the business is performing:

| Metric | Month 1 | Month 2 | Month 3 |
| --- | --- | --- | --- |
| Total Revenue | $250,000 | $220,000 | $200,000 |
| Customer Complaints | 45 | 60 | 80 |
| Food Waste (kg) | 300 kg | 420 kg | 510 kg |
| Online Orders | 500 | 380 | 290 |
| Staff Who Quit | 3 | 5 | 7 |

Looking at this data, it is clear that things are getting worse each month. Revenue is falling, complaints are rising, and staff are leaving.

3. Diagnostic Analysis

This step tries to find out why things are going wrong. After reviewing the data and talking to staff and customers, the following root causes were identified:

Why is revenue dropping?

- Customers are frustrated by slow checkout lines. Many are choosing to shop elsewhere.

- The online store is difficult to use and loads slowly, so customers give up before completing their order.

Why is food waste increasing?

- The store is ordering too much stock without checking what is actually selling.

- There is no proper system to track expiry dates and move products to discount shelves in time.

Why are staff leaving?

- Employees say they do not feel supported by management and are not given clear instructions.

- There is no proper onboarding process for new hires, so they feel lost and quit early.

4. Predictive Analysis

Based on the trends in the data, here is what is likely to happen if FreshMart does not make changes:

- Revenue could drop to $170,000 or less by Month 5 if customers keep leaving.

- Food waste could reach over 700 kg per month, costing the business thousands of dollars in losses.

- If staff keep quitting at the same rate, the stores will struggle to stay open properly during busy hours.

- Online orders will likely keep falling as long as the website remains slow and hard to use.

These are not guaranteed outcomes, but they are realistic if nothing changes based on the direction of the current numbers.

5. Prescriptive Analysis

This step recommends what FreshMart should do to fix the problems. These recommendations will guide the Agile project:

- Fix the checkout process — add more self-checkout machines and train staff to work faster at tills.

- Redesign the online ordering website to make it simpler and faster to use on mobile phones.

- Introduce a smart stock management system that tracks expiry dates and sends alerts when items need to be discounted.

- Create a proper staff onboarding and training programme so new employees feel welcome and know what to do.

- Set up a customer feedback system so FreshMart can hear complaints quickly and respond before customers leave for good.

6. Agile Methodology and Sprint Activities

Based on the prescriptive analysis, FreshMart will use the Scrum Agile methodology. Scrum is a good fit here because the problems are different from each other and can be worked on by separate teams at the same time. Each team will work in 2-week sprints.

There will be four teams, each focusing on one problem area:

Team 1 – Checkout & In-Store Experience

- Sprint 1: Observe current checkout process, talk to customers, and list all pain points.

- Sprint 2: Install two new self-checkout machines and trial them in one store.

- Sprint 3: Train staff on faster service techniques and measure improvement in wait times.

- Sprint 4: Review results, gather customer feedback, and roll out changes to all stores.

Team 2 – Website & Online Orders

- Sprint 1: Review the current website, identify what is making it slow and confusing.

- Sprint 2: Redesign the homepage and order flow to make it simpler and mobile-friendly.

- Sprint 3: Test the new site with a small group of customers and fix any reported issues.

- Sprint 4: Launch the updated website and track whether online orders increase.

Team 3 – Stock & Waste Management

- Sprint 1: Review current ordering habits and identify the most wasted product categories.

- Sprint 2: Introduce a basic expiry tracking sheet and trial it in two stores.

- Sprint 3: Set up a "near expiry" discount system to sell products before they go to waste.

- Sprint 4: Measure food waste levels after changes and report on cost savings.

Team 4 – Staff Training & Retention

- Sprint 1: Survey current staff to understand why they are unhappy or leaving.

- Sprint 2: Create a simple onboarding guide for new staff joining any FreshMart store.

- Sprint 3: Pilot a weekly team check-in meeting (like a Scrum standup) in two stores.

- Sprint 4: Review staff satisfaction scores and see if the quit rate has gone down.

7. Product Backlog Items

Here are four backlog items for this project:

| Item No. | Type | Description | Priority | Story Points | Status | Sprint | Assignee | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BL-001 | User Story | As a customer, I want a faster checkout so I can leave the store quickly without waiting in long queues. | High | 8 | In Progress | Sprint 1 | Checkout Team | Checkout wait time reduced to under 3 minutes; at least 80% of customers rate the experience positively. |
| BL-002 | Technical Improvement | Rebuild the online ordering page so it loads faster and works properly on mobile phones. | High | 13 | To Do | Sprint 2 | Website Team | Website loads in under 3 seconds; online orders increase by at least 15% within one sprint. |
| BL-003 | Spike | Research whether a low-cost stock tracking app can help staff manage expiry dates without needing expensive software. | Medium | 5 | To Do | Sprint 1 | Stock Team | A short report is produced comparing at least 3 options with costs, pros, and cons clearly listed. |
| BL-004 | Non-Functional Requirement | All new staff must be able to complete their first shift confidently after going through the onboarding guide. | Medium | 5 | To Do | Sprint 2 | HR Team | New hires score at least 7/10 on a confidence survey after their first week; manager confirms readiness. |

Note: Story points reflect the effort and complexity of each task. Higher points mean more work is involved.